## Prioritised Worklist
Request Type | Requestor | ELT Sponser | Task / Step | Request Id | Bus Case Id | Est. Days | < 8hrs | Type | Do we have to do it now? | Required Date | Estimated Start date | Priority | Strat Fit | Payback | IRR | Est Cost | Progress | Estimated End Date | Actual End Date | Days to finish | Developer | Comments
Small Work | Glen H | SMJ | Lync Phone reporting | 024 |  | 1 | YES | Enhancement | NO | 2015-08-30 |  | 2 |  |  |  | 1200 |  |  |  |  | HM
Small Work | Bronwyn R | SMJ | FMS Custom features | 023 |  | 1 | YES | Enhancement | NO | 2015-09-04 | 2015-09-03 | 3 |  |  |  | 1200 |  |  |  |  | HM
Small Work | Kieran P | GM / MJ | Enhancements to NAIT | 025 |  | 1 | YES | Enhancement | NO | 2015-10-01 |  | 4 |  |  |  | 1200 |  |  |  |  | RH
Small Work | Tania Y | LW | EA Request - Fixed Term Reason | 026 |  | 1 | YES | Enhancement | NO | 1899-12-31 |  | 5 |  |  |  | 1200 |  |  |  |  | RH
Small Work | Matthew K | PM | Fert Report Default Year Changes | 027 |  | 1 | YES | Enhancement | NO | 2015-10-01 |  | 6 |  |  |  | 1200 |  |  |  |  | RH
Small Work | Hayden M | MK | Fert Plan from TM1 |  |  | 1 | YES | Stay in Business | NO | 2015-09-14 |  | 7 |  |  |  | 1200 |  |  |  |  | HM
Small Work | David B | SMJ | Navision Reporting Layer Investigation | 008 |  | 1 | YES | Stay in Business | YES |  |  | 8 |  |  |  | 1200 |  |  |  |  | HM
Stay in Business | David B | SMJ | Migrate FMS & NAIT Database |  |  | 3 | NO | Stay in Business | NO | 2015-09-01 | 2015-08-18 | 1 |  |  |  | 3600 | 50% |  |  |  | RH
Stay in Business | David B | SMJ | Migrate FMS Reporting |  |  | 10 | NO | Stay in Business | NO | 2015-10-01 |  | 2 |  |  |  | 12000 |  |  |  |  | HM
Stay in Business | David B | SMJ | Migrate Mapping Web App |  |  | 1 | YES | Stay in Business | NO | 2015-11-01 |  | 3 |  |  |  | 1200 |  |  |  |  | HM
Stay in Business | David B | SMJ | Migrate Leases Web App |  |  | 1 | YES | Stay in Business | NO | 2016-01-01 |  | 4 |  |  |  | 1200 |  |  |  |  | HM
Stay in Business | David B | SMJ | Migrate Inventory Web App |  |  | 1 | YES | Stay in Business | NO | 2016-01-01 |  | 5 |  |  |  | 1200 |  |  |  |  | RH
Stay in Business | David B | SMJ | Migrate LPR Datasheets Web App |  |  | 1 | YES | Stay in Business | NO | 2016-01-01 |  | 6 |  |  |  | 1200 |  |  |  |  | RH
Stay in Business |  | PM | Water Meters - Phase 2 |  |  | 5 | NO | Compliance | YES | 2958465 | [5 empty] | 6000 | [5 empty] | Awaiting specs and Audit of meters on farms
Work List | David B | SMJ | FMS Usage Stats |  |  | 16 | NO | Enhancement | NO | 2015-08-31 | 2015-07-13 |  | 20 | 10 | 10 | 19200 | 97% | 2015-08-03 09:36 |  |  | HM
Work List | Huey V | MJ | DPR Pasture Growth Rate Forecaster | 004 |  | 15 | NO | Enhancement | NO | 2015-08-31 | 2015-07-29 |  | 9 |  |  | 18000 | 2% | 2015-08-18 |  |  | RH | Awaiting action from Mark J
Work List | Phil M | PM | DPR Widget - Water Usage | 003 |  | 5 | NO | Enhancement | NO | 2958465 |  |  | 5 |  |  | 6000 |  | 2958465 |  |  | HM | Dependant on Water Meters Phase 2 to be completed
Work List | Phil M | PM | DPR Widget - Electricity | 001 |  | 3 | NO | Enhancement | NO | 31/09/2015 | 2015-08-18 |  | 4 |  |  | 3600 | 95% | 2015-08-21 04:48 |  |  | HM
Work List | Phil M | PM | DPR Widget - Effluent | 002 |  | 4 | NO | Enhancement | NO | 31/09/2015 | 2015-09-01 |  | 18 |  |  | 4800 |  | 2015-09-05 14:24 |  |  | RH
Work List | Fintan P | MJ | Effluent Monitoring | 028 |  | 4 | NO | Enhancement | NO | 2015-09-01 | 2015-09-01 |  | 18 |  |  | 4800 | 40% | 2015-09-07 |  |  | RH
Work List | Kieran P | GM | Visibility of FMS livestock weighting event information | 021 |  | 3 | NO | Enhancement | NO | 2015-10-01 |  |  | 17 |  |  | 3600
Work List | PM & KP | MJ | Dairy Heifer Reporting | 012 |  | 10 | NO | Enhancement | NO | 2015-10-01 |  |  | 16 |  |  | 12000
Work List | Paul Mc | GM | Net Kg Product | 010 |  | 5 | NO | Enhancement | NO | 2015-12-01 |  |  | 15 |  |  | 6000
Work List | Heidi | ACB | Gateway Farm Home Pages |  |  | 10 | NO | Enhancement | NO | 31/09/2015 | [5 empty] | 12000 |  |  |  |  | HM
Work List | Heidi N | ACB | Supply Data for web page linking to gateway |  |  | 5 | NO | Enhancement | NO | [6 empty] | 6000
Work List | Phil M | PM | Feed Capture | 017 |  | 5 | NO | Enhancement | NO | [6 empty] | 6000
Work List | Phil M | PM | Energy report | 018 |  | 5 | NO | Enhancement | NO | [6 empty] | 6000
Work List | Phil M | PM | Nutrient Management | 019 |  | 5 | NO | Enhancement | NO | [6 empty] | 6000
Work List | Phil M | PM | Lease Report | 020 |  | 5 | NO | Enhancement | NO | [6 empty] | 6000
Work List | Claire H | SMJ | TrackIt & Lync reporting |  |  | 5 | NO | Enhancement | NO | [6 empty] | 6000
Oh Hold | Steve T | GM | Automation of Farm Return for Department of Stats | 016 |  | 16 | NO | Enhancement | NO | 2016-01-01 | [5 empty] | 19200
Delayed SIB | David B | SMJ | Weather Import ETL SQL 2012 Upgrade |  |  | 3 | NO | Stay in Business | NO | 2016-01-01 |  | 2 |  |  |  | 3600
Delayed SIB | David B | MJ | Milk Import ETL SQL 2012 Upgrade |  |  | 3 | NO | Stay in Business | NO | 2016-01-01 |  | 3 |  |  |  | 3600
Delayed SIB | David B | PM | Fert ETL SQL 2012 Upgrade |  |  | 5 | NO | Stay in Business | NO | 2016-01-01 |  | 4 |  |  |  | 6000
On Hold
| MK | GM | Fert Investigation (missing data) |  |  | 2 | NO | Stay in Business | YES | Unknown |  | 3 |  |  |  | 2400 | Complete
|  | LA | Employee Agreement - Min Wage |  |  | 0.1 | YES | Compliance | YES |  |  | 2 |  |  |  | 120 | Complete
|  | LA | Employee Agreement - Rename Field |  |  | 0.5 | YES | Enhancement | NO |  |  | 3 |  |  |  | 600 | Complete
| Tim S | SMJ | Fuel Returns |  |  | 10 | NO | Enhancement | NO |  |  |  | 20 | 10 | 10 | 12000 | Complete
|  | MJ | DPR ETL SQL 2012 Upgrade |  |  | 10 | NO | Stay in Business | YES | 2015-03-31 |  | 1 |  |  |  | 12000 | Complete
|  | MJ | DPR Dashboard - web development |  |  | 55 | NO | Stay in Business | YES | 2015-07-01 | 2015-04-01 | 2 |  |  |  | 66000 | Complete |  | 2015-06-25 | 61.4286
Small Work | Tania Y | ACB | Employment Agreement - Hourly Rate | 014 |  | 1 | YES | Enhancement | NO |  | 2015-07-10 | 2 |  |  |  | 1200 | 100% | 2015-07-10 09:36 | 2015-07-10 | 1 | HM
Small Work | Tania Y | ACB | Employment Agreement Process | 013 |  | 1 | YES | Enhancement | NO |  | 2015-07-10 | 3 |  |  |  | 1200 | 100% | 2015-07-10 09:36 | 2015-07-10 | 1 | HM
Small Work | Paul Mc | GM | Y/E Weight & LW Production reports | 007 |  | 1 | YES | Enhancement | NO |  | 2015-07-13 | 6 |  |  |  | 1200 | 100% | 2015-07-13 09:36 | 2015-08-03 | 15.7143 | HM | Took much longer due to having to rewrite a large part of the process due to finding lots of discrepancies
Small Work | BI Team | SMJ | FMS ETL changes |  |  | 1 | YES | Stay in Business | YES | 2015-03-18 | 2015-03-18 | 99 |  |  |  | 1200 | 100% | 2015-03-18 09:36 | 2015-03-18 | 1 | HM
Small Work | Huey V | MJ | DPR Growth rate graph | 005 |  | 1 | YES | Enhancement | NO |  | 2015-07-25 | 1 |  |  |  | 1200 | 100% | 2015-07-25 09:36 | 2015-07-27 | 3 | RH
Small Work | Huey V | MJ | DPR Widget - % MS to target | 006 |  | 1 | YES | Enhancement | NO |  | 2015-07-29 | 2 |  |  |  | 1200 | 100% | 2015-07-29 09:36 | 2015-07-31 | 3 | RH
Small Work |  |  | Skunk Work |  |  | 2 | NO | Enhancement | NO | 2015-08-12 | 2015-08-11 |  |  |  |  | 2400 | 100% | 2015-08-12 19:12 | 2015-08-12 | 2 | HM & RH
Delayed SIB | David B | ALL | IE11 testing |  |  | 5 | NO | Stay in Business | NO | 2015-06-30 | 2015-07-21 | 1 |  |  |  | 6000 | 100% | 2015-07-27 |  |  |  | Users are using currently using a Laptop with IE11 on it however this is not going to be full testing
Small Work | Brent H | SMJ | FMS Livestock Number Owned Integrity Check | 015 |  | 1 | YES | Enhancement | NO |  | 2015-08-14 | 2 |  |  |  | 1200 | 100% | 2015-08-14 09:36 | 2015-08-17 | 1 | HM
Small Work | Rachel H | GMPS | Kiosk User Pay Global Extract | 022 |  | 1 | YES | Stay in Business | YES | 2015-08-21 | 2015-08-19 | 1 |  |  |  | 1200 | 100% | 2015-08-21 | 2015-08-21 | 1 | HM
Work List | Peter J | PM | Farm Environment scorecard | 009 |  | 10 | NO | Enhancement | NO | 2015-08-01 | 2015-07-13 |  | 10 |  |  | 12000 | 100% | 2015-07-26 |  |  | RH
Work List | Tania Y | ACB | Request Form Attachments | 011 |  | 3 | NO | Enhancement | NO | 2015-08-21 | 2015-08-03 |  | 5 |  |  | 3600 | 100% | 2015-08-06 04:48 |  |  | RH
Small Work | David B | SMJ | Skunk follow up |  |  | 1 | YES | Enhancement | NO | 2015-09-01 | 2015-09-01 | 1 |  |  |  | 1200 | 100% |  |  |  | HM & RH
Formulas:
Estimated End Date = [Estimated Start date]+([Est. Days]/5*7)-1

## Projects
Id | Name | Requestor | Request Documentation
1 | DPR Widget - Electricity | Phil McKenzie | 001 - DPR Widget - Electricity.doc
2 | DPR Widget - Effluent | Phil McKenzie | 002 - DPR Widget - Effluent.doc
3 | DPR Widget - Water Usage | Phil McKenzie | 003 - DPR Widget - Water Usage.doc
4 | DPR Pasture Growth Rate Forecaster | Huey Van Vliet | 004 - DPR Pasture Growth Rate Forecaster .doc
5 | DPR Growth rate graph | Huey Van Vliet | 005 - DPR Growth rate graph.doc
6 | DPR Widget - % MS to target | Huey Van Vliet | 006 - DPR Widget - % MS to target.doc
7 | Y/E Weight & LW Production reports | Paul McGill | 007 - Copy of Closing Opening Weights Summary.xls
8 | Navision Reporting Layer Investigation | David Bailey
9 | Farm Environment scorecard | Peter Jordan | 009 - Environment Scorecard Request.doc
10 | Net Kg Product | Paul McGill | 010 - Kg Product.doc
11 | Request Form Attachments | Tania Yorwarth | 011 - Request Attachments .doc
12 | Dairy Heifer Reporting | Paul McGill | 012 - Visibility of FMS heifer grazing weights.docx
13 | Employment Agreement Process | Tania Yorwarth | 013 - Employment Agreement Process.doc
14 | Employment Agreement- Hourly Rate | Tania Yorwarth | 014 - Employment Agreement - Hourly Rate.doc
15 | FMS Livestock Number Owned Integrity Check | Brent Harris | 015 - FMS Livestock Number Owned Integrity Check.doc
16 | Automation of Farm Return for Department of Stats | Steve Tickner | 016 - Automation of Farm Return for Department of Stats.doc
17 | Feed Capture | Phil McKenzie | 017 - Feed Capture.doc
18 | Energy report | Phil McKenzie | 018 - Energy report.doc
19 | Nutrient Management | Phil McKenzie | 019 - Nutrient Management.doc
20 | Lease Report | Phil McKenzie | 020 - Lease Report.doc
21 | Visibility of FMS livestock weighting event information | Kieran Parsons | 021 - Visibility of FMS livestock weighing event information.docx
22 | Kiosk User Pay Global Extract | Rachel Hunter | 022 - Kiok User Pay Global Extract.doc
23 | FMS Custom Features | Bronwyn Rodgers | 023 - FMS Custom Features.doc
24 | Lync Phone reporting | Glen Heke | 024 - BI Work Request Lync Phone reporting for BST.doc
25 | NNS enhancements | Kieran Parsons | 025 - NNS enhancements.doc
26 | EA Request - Fixed Term Reason | Tania Yorwarth | 026 - EA Request - Fixed Term Reason.doc
27 | Fert Report Default Year Changes | Matthew Keltie | 027 - Fert Report Default Year Changes.doc
28 | Effluent Monitoring | Fintan Philips | 028 - Effluent Monitoring.doc
29
30
31
32
33

## Look Ups
Compliance | YES | Dev Costs | 150
Enhancement | NO
Stay in Business
On Hold

## Monthly
2015-09-08 |  | Next Prioritisation | 2015-08-17
Requestor | ELT Sponser | Task / Step | Request Id | Bus Case Id | Est. Days | < 8hrs | Type | Do we have to do it now? | Required Date | Estimated Start date | Priority | Strat Fit | Payback | IRR | Est Cost | Progress | Estimated End Date | Actual End Date | Days to finish | Developer | Comments
Work List (Currently working on)
David B | SMJ | FMS Usage Stats |  |  | 16 | NO | Enhancement | NO | 2015-08-31 | 2015-07-13 |  | 20 | 10 | 10 | 19200 | 90% | 2015-08-03 09:36 |  | 44.7857 | HM | Went over due to liveweight reporting taking precedence and over running. | Red
Peter J | PM | Farm Environment scorecard | 009 |  | 10 | NO | Enhancement | NO | 2015-08-01 | 2015-07-13 |  | 10 |  |  | 12000 | UAT | 2015-07-26 | 2015-08-10 | 15 | RH | Out for UAT * | Amber
Huey V | MJ | DPR Pasture Growth Rate Forecaster | 004 |  | 15 | NO | Enhancement | NO | 2015-08-31 | 2015-07-29 |  | 9 |  |  | 18000 | 2% | 2015-08-18 |  |  | RH | Awaiting action from Mark J | Green
Phil M | PM | DPR Widget - Water Usage | 003 |  | 5 | NO | Enhancement | NO | Unknown | 2015-10-01 |  | 5 |  |  | 6000 | 0% | 2015-10-07 |  |  | HM | Dependant on Water Meters Phase 2 to be completed | Green
Tania Y | ACB | Request Form Attachments | 011 |  | 3 | NO | Enhancement | NO | 2015-08-21 | 2015-08-03 |  | 5 |  |  | 3600 | 90% | 2015-08-06 04:48 |  | 28.2857 | RH | * | Red
Completed Work
Tania Y | ACB | Employment Agreement - Hourly Rate | 014 |  | 1 | YES | Enhancement | NO |  | 2015-07-10 | 2 |  |  |  | 1200 | Complete | 2015-07-10 09:36 | 2015-07-10 | 1 | HM |  | Green
Tania Y | ACB | Employment Agreement Process | 013 |  | 1 | YES | Enhancement | NO |  | 2015-07-10 | 3 |  |  |  | 1200 | Complete | 2015-07-10 09:36 | 2015-07-10 | 1 | HM |  | Green
Paul Mc | GM | Y/E Weight & LW Production reports | 007 |  | 1 | YES | Enhancement | NO |  | 2015-07-13 | 6 |  |  |  | 1200 | Complete | 2015-07-13 09:36 | 2015-08-03 | 15.7143 | HM | Took much longer due to having to rewrite a large part of the process due to finding lots of discrepancies | Red
BI Team | SMJ | FMS ETL changes |  |  | 1 | YES | Stay in Business | YES | 2015-03-18 | 2015-03-18 | 99 |  |  |  | 1200 | Complete | 2015-03-18 09:36 | 2015-03-18 | 1 | HM |  | Green
Huey V | MJ | DPR Growth rate graph | 005 |  | 1 | YES | Enhancement | NO |  | 2015-07-25 | 1 |  |  |  | 1200 | Complete | 2015-07-25 09:36 | 2015-07-27 | 3 | RH | * | Red
Huey V | MJ | DPR Widget - % MS to target | 006 |  | 1 | YES | Enhancement | NO |  | 2015-07-29 | 2 |  |  |  | 1200 | Complete | 2015-07-29 09:36 | 2015-07-31 | 1.5 | RH | * | Amber
|  | Skunk Work |  |  | 2 | NO | Enhancement | NO | 2015-08-12 | 2015-08-11 |  |  |  |  | 2400 | Complete | 2015-08-12 19:12 | 2015-08-12 | 2 | HM & RH |  | Green
David B | ALL | IE11 testing |  |  | 5 | NO | Stay in Business | NO | 2015-06-30 | 2015-07-21 | 1 |  |  |  | 6000 | Complete | 2015-07-27 |  | 2 |  |  | Green
Brent H | SMJ | FMS Livestock Number Owned Integrity Check | 015 |  | 1 | YES | Enhancement | NO |  | 2015-08-14 | 2 |  |  |  | 1200 |  |  |  |  | HM |  | Green
* On boarding of new staff member has taken up time with training and explaining how things work.
Formulas:
Estimated End Date = [Estimated Start date]+([Est. Days]/5*7)-1
Days to finish = IF([Actual End Date]="",(TODAY() -[Estimated Start date]) /7*5, "") * (1 + (1-[Progress]))

## Prioritisation
Items to be prioritised
20
ID | Requestor | Sponser | Name | Est Effort | People | Enviroment | Volume | value | Efficiency | TOTAL
010 | Paul M | GM | Net Kg Product | 5 | [5 empty] | 15
012 | PM & KP | MJ | Dairy Heifer Reporting | 10 | [5 empty] | 16
016 | Steve T | GM | Automation of Farm Return for Department of Stats | 16 | [5 empty] | 0
021 | Kieran P | GM | Visibility of FMS livestock weighting event information | 16 | [5 empty] | 17
002 | Phil M | PM | DPR Widget - Effluent | 4 | [5 empty] | 18